## Phase Tasks
Phase | Phase Name | Description | Key Deliverables
1 | Project Foundation | Repository setup, architecture design, environment configuration | Repo initialized, architecture skeleton, env config, basic service running
2 | Data Engine | Historical data ingestion from Kite API, instrument master, watchlists | Data collector, instrument table, watchlist manager, caching layer
3 | Strategy Engine | Strategy interface, indicators, parameter framework | Strategy base class, indicator library, parameter system
4 | Backtesting Engine | Trade simulator, order execution logic, performance metrics | Backtest runner, trade logs, performance statistics
5 | Optimization Engine | Parameter grid search and walk-forward optimization | Parameter sweeper, optimization reports, best-parameter ranking
6 | UX / Frontend | Strategy list, watchlists UI, parameter editor, result charts | Strategies page, watchlists page, annotated backtest charts
7 | Broker Integration | Zerodha/Kite settings UI and connectivity similar to SigmaTrader | Broker settings page, token management, connection validation
8 | Visualization & Reporting | Equity curve, drawdown charts, trade markers | Interactive charts, exportable reports
9 | Deployment | Docker setup, logging, monitoring, production configuration | Docker image, logging pipeline, production config